## Slide 1: PFAS Treatment Systems Update Design and Construction

## Slide 3
Design
Construction
62 Wells : 34 Operational and 28 Design/Construction
Out to bid

## Slide 5: Need irwd pic

## Slide 8
La Palma
Boysen Park
Energy Field
Linda Vista
Anaheim Phase A

## Slide 9
Boysen Park
Well 46 rehab is expected to be completed this month and the VFD is expected to arrive then as well. CDM is working on electrical in order to install the VFD when it arrives. Commissioning to begin in December.

## Slide 10
Anaheim Phase B
Santa Cruz
Willow Park
Brookhurst
Downtown
Katella

## Slide 11
Wells 60 and 61 building construction is underway and installation of electrical equipment continues. Work on the 24-inch Orangewood pipeline continues.
Santa Cruz

## Slide 12
Well 40 rehab has begun. Installation of underground utilities and work on the building modifications continues.
Brookhurst
Well 40 rehab has begun. Installation of underground utilities and work on the building modifications continues

## Slide 13
Above ground piping and appurtenance installation continues. Electrical work continues.
Downtown

## Slide 14
Installation of electrical equipment and other utilities continues.
Katella

## Slide 15
Tustin Wells

## Slide 16
Conveyance Pipeline
Distribution Pipeline

## Slide 17
Contractor continued primarily with underground electrical.

## Slide 18
Questions?

## Slide 19: Fullerton Main Plant
F-7A

## Slide 20
New Well 7A
(Separate City Project)
F-3A
F-5
F-8
F-6
F-7
Distribution
Distribution